## Year 1 Roadmap
STUDENT ROADMAP TEMPLATE ¦ YEAR 1
Enter tasks or deliverables in separate rows. Show milestones directly in the relevant month using ◆ plus the milestone name.
Project / Case: |  |  | Team members: |  |  |  | Academic year: |  |  | Currency: | EUR
PILLAR / OBJECTIVE | INITIATIVE | TASK / DELIVERABLE | RESPONSIBLE | SUCCESS METRIC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | COST TYPE | ESTIMATED COST (€) | EXPECTED BENEFIT (€) | NET FINANCIAL IMPACT (€) | FINANCIAL IMPACT NOTES | ASSUMPTIONS / DEPENDENCIES | STATUS | PRIORITY
Digital Infrastructure | Deploy low-power field sensors | Install and validate pilot sensors at selected locations | IoT Project Lead | Pilot acceptance criteria achieved; at least 95% sensor connectivity | JAN: ● Plan; FEB: ● Install; Academic year: MAR: ◆ Pilot completed | Technology | 25000 | 10000 | -15000 | Year 1 benefit from reduced manual monitoring | Pilot locations and network coverage confirmed | Planned | High

## Financial Summary
YEAR 1 FINANCIAL IMPACT SUMMARY
Metric | Value | Interpretation
Total estimated cost | 25000 | Total planned investment or expenditure
Total expected benefit | 10000 | Expected quantifiable financial benefit
Net financial impact | -15000 | Expected benefit minus estimated cost
Benefit-cost ratio | 0.4 | Expected benefit generated per euro of cost
Items with financial data | 2 | Number of cost and benefit values entered
Financial-impact guidance
Estimated cost | Enter the direct Year 1 cost attributable to the row. Avoid counting the same cost in both an initiative and its underlying tasks.
Expected benefit | Enter only a quantified Year 1 financial benefit. Non-financial outcomes belong in Success Metric or Financial Impact Notes.
Net financial impact | Calculated automatically as expected benefit minus estimated cost.
Milestones | Milestones may have their own cost or benefit when a payment, funding release, saving or revenue event is tied to the gate.
Tasks | Use a separate row when a task has a distinct owner, timing, cost or measurable output.

## Student Instructions
HOW TO COMPLETE THE ROADMAP
1 | Define pillars | Enter the strategic themes or objectives that organize the roadmap.
2 | Add initiatives | Enter the main projects or coordinated bodies of work under each pillar.
3 | Add tasks and milestones | Enter each task or deliverable in its own row. Show a milestone directly in the relevant month using ◆ followed by a short achievement name, for example ◆ Pilot completed.
4 | Plan Year 1 | Use ● in the months when work is active. Use ◆ plus the milestone name in the month when the key achievement or decision occurs.
5 | Assign accountability | Name one responsible owner and define a measurable success criterion for each row.
6 | Estimate financial impact | Choose the cost type, enter estimated cost and expected benefit, and document assumptions.
7 | Review totals | Check Financial Summary and make sure costs are not duplicated between initiatives, milestones and tasks.