## Roadmap with Milestones
PILLAR-BASED DELIVERY ROADMAP ¦ MILESTONES + TASKS
Contributors: |  |  | Version date:
Milestone labels supplied in the source are retained. Labels not visible in the source are working labels and should be confirmed before baselining.
PILLAR / OBJECTIVE | INITIATIVE | MILESTONE LABELS | TASKS / DELIVERABLES | RESPONSIBLE | SUCCESS METRIC | 2026 Q1 | 2026 Q2 | 2026 Q3 | 2026 Q4 | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4 | START | END
Data & IoT Infrastructure | Deploy low-power field sensors | Pilot – 26 Q1; Scale – 26 Q3 | See task rows below | TBD | Define measurable outcome / KPI | ◆ Pilot |  | ◆ Scale | [9 empty] | 2026 Q1 | 2026 Q3
| Task 1 |  | Define pilot scope and target locations | TBD | TBD
| Task 2 |  | Install and connect pilot sensors | TBD | TBD
| Task 3 |  | Validate pilot results and acceptance criteria | TBD | TBD
| Task 4 |  | Scale deployment to agreed locations | TBD | TBD
Data & IoT Infrastructure | Edge + LoRaWAN network build-out | Start gate – 26 Q2; Completion gate – 26 Q4 | See task rows below | TBD | Define measurable outcome / KPI |  | ◆ Start gate |  | ◆ Completion gate | [8 empty] | 2026 Q2 | 2026 Q4
| Task 1 |  | Confirm architecture and coverage requirements | TBD | TBD
| Task 2 |  | Procure/configure gateways and edge components | TBD | TBD
| Task 3 |  | Deploy and test LoRaWAN connectivity | TBD | TBD
| Task 4 |  | Complete operational handover | TBD | TBD
Data & IoT Infrastructure | Unified Data Lake & Stream Ingestion | Start gate – 26 Q3; Release gate – 27 Q1 | See task rows below | TBD | Define measurable outcome / KPI |  |  | ◆ Start gate |  | ◆ Release gate | [7 empty] | 2026 Q3 | 2027 Q1
| Task 1 |  | Define data sources and ingestion requirements | TBD | TBD
| Task 2 |  | Build ingestion pipelines | TBD | TBD
| Task 3 |  | Configure data quality and monitoring | TBD | TBD
| Task 4 |  | Validate unified data availability | TBD | TBD
Farm Operations | Variable-rate irrigation V1 | Design gate – 26 Q4; V1 release – 27 Q3 | See task rows below | TBD | Define measurable outcome / KPI |  |  |  | ◆ Design gate |  |  | ◆ V1 release | [5 empty] | 2026 Q4 | 2027 Q3
| Task 1 |  | Define agronomic and technical requirements | TBD | TBD
| Task 2 |  | Build irrigation control logic | TBD | TBD
| Task 3 |  | Run field validation | TBD | TBD
| Task 4 |  | Release V1 and document results | TBD | TBD
Farm Operations | Computer Vision Pest & Disease Detection | PoC start – 27 Q1; Validation gate – 27 Q4 | See task rows below | TBD | Define measurable outcome / KPI |  |  |  |  | ◆ PoC start |  |  | ◆ Validation gate |  |  |  |  | 2027 Q1 | 2027 Q4
| Task 1 |  | Collect and label image data | TBD | TBD
| Task 2 |  | Train and evaluate detection model | TBD | TBD
| Task 3 |  | Integrate field capture workflow | TBD | TBD
| Task 4 |  | Validate detection performance | TBD | TBD
Farm Operations | Autonomous scouting drones (PoC) | PoC start – 27 Q1; PoC decision – 28 Q1 | See task rows below | TBD | Define measurable outcome / KPI |  |  |  |  | ◆ PoC start |  |  |  | ◆ PoC decision |  |  |  | 2027 Q1 | 2028 Q1
| Task 1 |  | Define scouting use cases and flight constraints | TBD | TBD
| Task 2 |  | Configure drone and sensor payload | TBD | TBD
| Task 3 |  | Execute controlled field trials | TBD | TBD
| Task 4 |  | Assess PoC results and scale decision | TBD | TBD
Market Access & Services | Farmer Mobile App (advice, alerts, logs) | Prototype – 26 Q2; Pilot release – 26 Q4 | See task rows below | TBD | Define measurable outcome / KPI |  | ◆ Prototype |  | ◆ Pilot release | [8 empty] | 2026 Q2 | 2026 Q4
| Task 1 |  | Define priority user journeys | TBD | TBD
| Task 2 |  | Design and build mobile experience | TBD | TBD
| Task 3 |  | Integrate advice, alert and logging services | TBD | TBD
| Task 4 |  | Test with pilot users and release | TBD | TBD
Market Access & Services | Input marketplace integration | Integration start – 26 Q3; Go-live gate – 27 Q3 | See task rows below | TBD | Define measurable outcome / KPI |  |  | ◆ Integration start |  |  |  | ◆ Go-live gate | [5 empty] | 2026 Q3 | 2027 Q3
| Task 1 |  | Define partner and catalogue requirements | TBD | TBD
| Task 2 |  | Design integration interfaces | TBD | TBD
| Task 3 |  | Build and test transaction flows | TBD | TBD
| Task 4 |  | Complete partner acceptance and go-live | TBD | TBD
Market Access & Services | Carbon credit measurement & issuance | Methodology gate – 26 Q4; Measurement gate – 27 Q3; Issuance gate – 28 Q2 | See task rows below | TBD | Define measurable outcome / KPI |  |  |  | ◆ Methodology gate |  |  | ◆ Measurement gate |  |  | ◆ Issuance gate |  |  | 2026 Q4 | 2028 Q2
| Task 1 |  | Define measurement methodology and evidence | TBD | TBD
| Task 2 |  | Implement carbon data collection | TBD | TBD
| Task 3 |  | Complete verification readiness checks | TBD | TBD
| Task 4 |  | Support credit issuance process | TBD | TBD
Platform & Org. Enablement | APIs & partner portal | API design gate – 26 Q3; Portal release – 27 Q1 | See task rows below | TBD | Define measurable outcome / KPI |  |  | ◆ API design gate |  | ◆ Portal release | [7 empty] | 2026 Q3 | 2027 Q1
| Task 1 |  | Prioritize partner use cases | TBD | TBD
| Task 2 |  | Define API and access standards | TBD | TBD
| Task 3 |  | Build APIs and partner portal | TBD | TBD
| Task 4 |  | Test onboarding and publish documentation | TBD | TBD
Platform & Org. Enablement | Data Governance & privacy (GDPR) | Governance design – 26 Q2; Compliance gate – 26 Q4 | See task rows below | TBD | Define measurable outcome / KPI |  | ◆ Governance design |  | ◆ Compliance gate | [8 empty] | 2026 Q2 | 2026 Q4
| Task 1 |  | Define data ownership and classification | TBD | TBD
| Task 2 |  | Document privacy and retention controls | TBD | TBD
| Task 3 |  | Implement access and consent requirements | TBD | TBD
| Task 4 |  | Complete governance/compliance review | TBD | TBD
Platform & Org. Enablement | Change Mgmt & Agro Enablement | Readiness start – 27 Q1; Adoption gate – 27 Q3 | See task rows below | TBD | Define measurable outcome / KPI |  |  |  |  | ◆ Readiness start |  | ◆ Adoption gate | [5 empty] | 2027 Q1 | 2027 Q3
| Task 1 |  | Identify impacted roles and stakeholders | TBD | TBD
| Task 2 |  | Prepare communications and training | TBD | TBD
| Task 3 |  | Deliver enablement activities | TBD | TBD
| Task 4 |  | Measure adoption and close readiness gaps | TBD | TBD
Sustainability & Compliance | Traceability & Audits (GSI/ISO) | Control design – 26 Q4; Audit readiness – 27 Q2 | See task rows below | TBD | Define measurable outcome / KPI |  |  |  | ◆ Control design |  | ◆ Audit readiness | [6 empty] | 2026 Q4 | 2027 Q2
| Task 1 |  | Map traceability requirements | TBD | TBD
| Task 2 |  | Implement evidence and control records | TBD | TBD
| Task 3 |  | Run internal readiness review | TBD | TBD
| Task 4 |  | Close gaps before external audit | TBD | TBD
Sustainability & Compliance | Water-use & nutrient dashboards | Dashboard design – 27 Q2; Release gate – 27 Q4 | See task rows below | TBD | Define measurable outcome / KPI | [5 empty] | ◆ Dashboard design |  | ◆ Release gate |  |  |  |  | 2027 Q2 | 2027 Q4
| Task 1 |  | Define measures and data sources | TBD | TBD
| Task 2 |  | Develop dashboard and calculations | TBD | TBD
| Task 3 |  | Validate results with business users | TBD | TBD
| Task 4 |  | Release dashboard and establish ownership | TBD | TBD

## Mapping Guide
TRANSLATION RULES
ROADMAP ELEMENT | NEW TEMPLATE LOCATION | HOW IT IS REPRESENTED | EXAMPLE
Pillar | Pillar / Objective | One colour-coded workstream grouping its initiatives | Data & IoT Infrastructure
Initiative bar | Initiative row | Summary row with duration across quarters | Deploy low-power field sensors
Named diamond | Milestone Labels + timeline cell | Label shown in text column and beside the diamond | Pilot Q1’26; Scale Q3’26
Work needed | Tasks / Deliverables | Four editable task rows under every initiative | Install and connect pilot sensors
Accountability | Responsible | Owner can be entered at initiative and task level | TBD
Outcome | Success Metric | Metric can be entered at initiative and task level | Pilot acceptance achieved

## Sheet3
Contributors: |  |  |  | Date: |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE
OBJECTIVES |  |  |  | MILESTONES (Examples) |  |  | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week
OBJECTIVES |  |  |  | MAIN OBJECTIVE:
Goal 1.1:
Goal 1.2:
Product |  | AGRICULTURE - PILOT PROJECT |  | Baseline Data Collection |  | Tasks
Responsable and Metrics
|  |  |  | Tech Partnerships |  | Tasks
Responsable and Metrics
|  |  |  | Preparation of Systems |  | Tasks
Responsable and Metrics
|  |  |  | Production Plan |  | Tasks
Responsable and Metrics
|  |  |  | Initial regulatory Permits |  | Tasks
Responsable and Metrics
|  | INDUSTRIAL - PILOT PROJECT IN FULL PRODUCTION MODE |  | Tecnhology Partnership |  | Tasks
Responsable and Metrics
|  |  |  | Rent a Processing Facility or Refurbish existing one |  | Tasks
Responsable and Metrics
|  |  |  | Buy or rent Equipment |  | Tasks
Responsable and Metrics
|  |  |  | Industrial Machinery Preparation /Assembly |  | Tasks
Responsable and Metrics
|  |  |  | Commissioning and Testing Processes |  | Tasks
Responsable and Metrics
Market |  | SCIENTIFIC - BEGIN THE PILOT TESTING PHASE OF THE R&D PROJECT |  | Established Key Scientific and Technological Partnerships |  | Tasks
Responsable and Metrics
|  |  |  | Risk Management Plan |  | Tasks
Responsable and Metrics
|  |  |  | R&D Plan for Human Consumption |  | Tasks
Responsable and Metrics
|  |  |  | R&D Plan for Animal Consumption |  | Tasks
Responsable and Metrics
|  |  |  | Set Pilot Measurable variables & data collection technology/system |  | Tasks
Responsable and Metrics
|  | MARKETS - PREPARED TO SELL ANIMAL FEED. GO TO MARKET PLAN FOR PROTEIN FOR HUMAN CONSUMPTION |  | Select First Products to introduce in the Market |  | Tasks
Responsable and Metrics
|  |  |  | Testing Plan for Animal Feed |  | Tasks
Responsable and Metrics
|  |  |  | Marketing Material, Branding & Communication |  | Tasks
Responsable and Metrics
|  |  |  | Contact Potencial Customers |  | Tasks
Responsable and Metrics
|  |  |  | Sampling Plan for Human Consumption |  | Tasks
Responsable and Metrics
Business Management |  | REGULATORY - OBTAIN ICNF PERMIT FOR THE PILOT PROJECT. KICK-OFF OF REGISTRATION AND CERTIFICATION PROCESSES |  | Permit for scientific use only |  | Tasks
Responsable and Metrics
|  |  |  | Animal Consumption - Feed Materials Register |  | Tasks
Responsable and Metrics
|  |  |  | Human Consumption - Novell Food Certification Process |  | Tasks
Responsable and Metrics
|  |  |  | Intelectual Property Protection Plan |  | Tasks
Responsable and Metrics
|  | FUNDS & RESOURCES - HAVE A FULLY FINANCED PILOT PROJECT AND ALL THE KEY RESOURCES |  | Land, Water & Power Source |  | Tasks
Responsable and Metrics
|  |  |  | Human Resources |  | Tasks
Responsable and Metrics
|  |  |  | Funding |  | Tasks
Responsable and Metrics
|  |  |  | Budget Preparation |  | Tasks
Responsable and Metrics
|  |  |  | Management Actions |  | Tasks
Responsable and Metrics
| BUDGET | FIXED COSTS (€/MONTH) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | VARIABLE COSTS (€) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | CAPEX (€) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  | ACCUMULATED COSTS + CAPEX (€) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Personnel | 0
|  |  | Consumables | 0
|  |  | Equipment and Software | 0
|  |  | Subcontracting | 0
|  |  | Others | 0
|  |  | TOTAL | 0