## Year 1 Roadmap
STUDENT ROADMAP TEMPLATE ¦ YEAR 1
Tasks are grouped by Pillar and Initiative. Month cells show the specific activity (● + short label); milestones are shown as ◆ + milestone name.
Project / Case: |  |  | Team members: |  |  |  | Academic year: |  |  | Currency: | EUR
PILLAR / OBJECTIVE | INITIATIVE | TASK / DELIVERABLE | RESPONSIBLE | SUCCESS METRIC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | COST TYPE | ESTIMATED COST (€) | EXPECTED BENEFIT (€) | NET FINANCIAL IMPACT (€) | FINANCIAL IMPACT NOTES | ASSUMPTIONS / DEPENDENCIES | STATUS | PRIORITY
Data & IoT Infrastructure | Deploy low-power field sensors | Define pilot scope and select target locations | IoT Project Lead | Pilot scope and locations formally approved | JAN: ● Scope | People/time | 3000 | 0 | -3000 | Planning effort | Site access available | Completed | High
|  | Install and connect pilot sensors | Field Technology Lead | All pilot sensors installed and transmitting data | FEB: ● Install; Academic year: MAR: ◆ Pilot completed | Technology | 25000 | 10000 | -15000 | Reduced manual monitoring | Network coverage confirmed | Completed | High
|  | Validate pilot results against acceptance criteria | Data & Analytics Lead | At least 95% sensor connectivity and agreed data quality | Academic year: APR: ● Validate | People/time | 5000 | 0 | -5000 | Validation effort | Four weeks of representative data | Planned | High
|  | Scale deployment to agreed locations | Deployment Lead | Scaled solution operational at all approved locations | Academic year: MAY: ● Deploy; Currency: JUN: ● Deploy; EUR JUL: ◆ Scale completed | Technology | 60000 | 30000 | -30000 | Operational efficiency benefit | Pilot acceptance achieved | Not started | High
| Edge + LoRaWAN network build-out | Confirm architecture and coverage requirements | Network Architect | Architecture and coverage design approved | FEB: ● Design | External services | 7000 | 0 | -7000 | Architecture support | Site survey data available | Completed | High
|  | Procure and configure gateways and edge components | Infrastructure Lead | Required gateways configured and ready for installation | Academic year: MAR: ● Procure / configure; Academic year: APR: ● Procure / configure | CAPEX | 40000 | 0 | -40000 | Network hardware investment | Procurement lead times accepted | In progress | High
|  | Deploy and test LoRaWAN connectivity | Network Operations Lead | Target coverage and connection stability achieved | Academic year: MAY: ● Deploy / test; Currency: JUN: ◆ Coverage validated | Technology | 18000 | 15000 | -3000 | Reduced connectivity failures | Installation access confirmed | Planned | High
|  | Complete operational handover | Service Operations Lead | Support documentation accepted and monitoring active | EUR JUL: ◆ Operational handover | Training | 6000 | 0 | -6000 | Training and handover cost | Support team availability | Not started | Medium
| Unified Data Lake & Stream Ingestion | Define data sources and ingestion requirements | Data Product Owner | Priority sources and data requirements approved | Academic year: APR: ● Requirements | People/time | 5000 | 0 | -5000 | Requirements effort | Source owners identified | Planned | High
|  | Build ingestion pipelines | Data Engineering Lead | Priority sources ingested automatically | Academic year: MAY: ● Build pipelines; Currency: JUN: ● Build pipelines; EUR JUL: ● Build pipelines | External services | 35000 | 20000 | -15000 | Automation and reduced manual processing | Source interfaces remain stable | Not started | High
|  | Configure data quality controls and monitoring | Data Governance Lead | Quality rules and pipeline alerts operational | EUR AUG: ● Quality controls; EUR SEP: ● Quality controls | Technology | 12000 | 10000 | -2000 | Fewer data-quality corrections | Data-quality thresholds agreed | Not started | Medium
|  | Validate unified data availability | Data Product Owner | Approved datasets available for reporting and analytics | EUR OCT: ◆ Data platform release | People/time | 5000 | 25000 | 20000 | Faster analytics and reporting | Business validation completed | Not started | High
Farm Operations | Variable-rate irrigation V1 | Define agronomic and technical requirements | Agronomy Product Lead | Irrigation requirements and target fields approved | JAN: ● Requirements; FEB: ● Requirements | People/time | 6000 | 0 | -6000 | Requirements and field consultation | Agronomy experts available | Completed | High
|  | Build irrigation control logic | Solution Engineering Lead | Control logic implemented for agreed scenarios | Academic year: MAR: ● Build logic; Academic year: APR: ● Build logic; Academic year: MAY: ● Build logic | Technology | 30000 | 18000 | -12000 | Reduced water and energy use | Sensor data is reliable | In progress | High
|  | Run field validation | Field Operations Lead | Field tests demonstrate agreed irrigation accuracy | Currency: JUN: ● Field test; EUR JUL: ● Field test; EUR AUG: ◆ Field validation completed | External services | 15000 | 12000 | -3000 | Avoided water and crop-loss costs | Seasonal test conditions available | Planned | High
|  | Release V1 and document operating model | Product Owner | V1 released with support and user documentation | EUR SEP: ◆ V1 released | Training | 8000 | 25000 | 17000 | Operational savings after adoption | Field validation passed | Not started | High
| Computer Vision Pest & Disease Detection | Collect and label image data | Data Science Lead | Representative labelled dataset approved | FEB: ● Collect / label; Academic year: MAR: ● Collect / label; Academic year: APR: ● Collect / label | External services | 20000 | 0 | -20000 | Data collection and annotation | Field image consent and access | In progress | High
|  | Train and evaluate detection model | Machine Learning Lead | Model achieves agreed precision and recall thresholds | Academic year: MAY: ● Train / evaluate; Currency: JUN: ● Train / evaluate; EUR JUL: ● Train / evaluate | Technology | 30000 | 20000 | -10000 | Earlier detection reduces crop loss | Label quality is sufficient | Not started | High
|  | Integrate field capture workflow | Mobile Product Lead | Field images captured and submitted through working workflow | EUR AUG: ● Integrate; EUR SEP: ● Integrate | Technology | 18000 | 10000 | -8000 | Reduced manual inspection effort | Mobile connectivity available | Not started | Medium
|  | Validate detection performance in the field | Agronomy Product Lead | Field validation signed off by agronomy experts | EUR OCT: ● Field validate; EUR NOV: ◆ Model validated | People/time | 10000 | 30000 | 20000 | Reduced treatment delay and crop loss | Representative pest cases available | Not started | High
| Autonomous scouting drones (PoC) | Define scouting use cases and flight constraints | Drone PoC Lead | Use cases, safety constraints and test sites approved | Academic year: MAR: ● Define use cases | People/time | 5000 | 0 | -5000 | PoC scoping effort | Flight permissions obtainable | Planned | Medium
|  | Configure drone and sensor payload | Drone Engineering Lead | Drone platform configured for selected scouting use cases | Academic year: APR: ● Configure; Academic year: MAY: ● Configure | CAPEX | 45000 | 0 | -45000 | Drone and imaging equipment | Vendor components available | Not started | Medium
|  | Execute controlled field trials | Field Operations Lead | Planned field missions completed with usable data | Currency: JUN: ● Field trials; EUR JUL: ● Field trials; EUR AUG: ● Field trials | External services | 18000 | 12000 | -6000 | Reduced manual scouting effort | Weather and flight access suitable | Not started | Medium
|  | Assess PoC results and make scale decision | Operations Steering Group | Documented go/no-go decision supported by trial evidence | EUR SEP: ◆ PoC decision | People/time | 4000 | 0 | -4000 | Decision preparation | Field-trial evidence complete | Not started | High
STUDENT PRACTICE AREA — Create additional pillars, initiatives, tasks and milestones below

## Financial Summary
YEAR 1 FINANCIAL IMPACT SUMMARY
Metric | Value | Interpretation
Total estimated cost | 430000 | Total planned investment or expenditure
Total expected benefit | 237000 | Expected quantifiable financial benefit
Net financial impact | -193000 | Expected benefit minus estimated cost
Benefit-cost ratio | 0.55116 | Expected benefit generated per euro of cost
Items with financial data | 48 | Number of cost and benefit values entered
Financial-impact guidance
Estimated cost | Enter the direct Year 1 cost attributable to the row. Avoid counting the same cost in both an initiative and its underlying tasks.
Expected benefit | Enter only a quantified Year 1 financial benefit. Non-financial outcomes belong in Success Metric or Financial Impact Notes.
Net financial impact | Calculated automatically as expected benefit minus estimated cost.
Milestones | Milestones may have their own cost or benefit when a payment, funding release, saving or revenue event is tied to the gate.
Tasks | Use a separate row when a task has a distinct owner, timing, cost or measurable output.
Note | The summary includes the two worked examples and any additional student rows. Delete or zero the example values if students need totals for their own roadmap only.

## Student Instructions
HOW TO COMPLETE THE ROADMAP
1 | Define pillars | Enter the strategic themes or objectives that organize the roadmap.
2 | Add initiatives | Enter the main projects or coordinated bodies of work under each pillar.
3 | Add tasks and milestones | Enter each task or deliverable in its own row. Show a milestone directly in the relevant month using ◆ followed by a short achievement name, for example ◆ Pilot completed.
4 | Plan Year 1 | Month cells include a short activity label such as ● Install or ● Validate. A milestone is shown as ◆ plus the achievement name, for example ◆ Pilot completed.
5 | Assign accountability | Name one responsible owner and define a measurable success criterion for each row.
6 | Estimate financial impact | Choose the cost type, enter estimated cost and expected benefit, and document assumptions.
7 | Review totals | Check Financial Summary and make sure costs are not duplicated between initiatives, milestones and tasks.
Worked examples | Two complete pillars | The roadmap contains two fully populated pillars, six initiatives and twenty-four task rows. Students should study how tasks, active months, milestone diamonds, ownership, success measures and financial impact connect.
Grouping | Pillars and initiatives | Repeated Pillar and Initiative cells are merged vertically. Every task remains on a separate row so ownership, timing, metrics and financial impact stay visible.